## Sheet1
Description | Start Date | Duration
Introduction | 2017-02-08 | 14
Logo and team name | 2017-02-08 | 2
Project Plan draft | 2017-02-12 | 2
Setup document | 2017-02-13 | 4
Determine system structure | 2017-02-13 | 7
Determine use cases | 2017-02-20 | 2
Design | 2017-02-22 | 35
Database design | 2017-02-22 | 2
Website design | 2017-02-24 | 6
Database implementation | 2017-03-06 | 3
Project Plan | 2017-03-10 | 11
Application design | 2017-03-13 | 5
Setup document | 2017-03-19 | 10
Functionality | 2017-04-18 | 42
Website link to database | 2017-04-18 | 7
Application functionality | 2017-04-18 | 21
Database rules and constraints | 2017-04-24 | 7
Website registration functionality | 2017-05-01 | 21
Database dependant applications | 2017-05-08 | 21
Website social media function | 2017-05-21 | 7
Database data | 2017-05-21 | 7
Conclusion | 2017-05-28 | 10
Project Review | 2017-05-28 | 5
Final testing | 2017-06-01 | 5
Release version | 2017-06-07 | 1